## ProjectSchedule
Automation of Concrete Mix Design | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
Nebraska Department of Transportation (NDOT) |  | Project Start: | 2026-01-16
Ava Johnson, Noah Morland |  | Today: | 2026-02-24
Jacob Lamorreaux, Ayub Abdi |  | Display Week: | 5 |  |  | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
 | time axis 2026-02-09 to 2026-04-05
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-02-09 to 2026-04-05
Phase 1 Technical
Complete in class Labs | All | 100% | 2026-02-06 | 2026-02-20 | 15
Draft SOW | Ava Johnson | 100% | 2026-02-13 | 2026-02-21 | 9
Phase 2 Required Submissions
Gantt Chart | Ava Johnson | 100% | 2026-02-06 | 2026-02-13 | 8
Flow Diagram | Ava Johnson and Noah Morland | 100% | 2026-02-13 | 2026-02-20 | 8
Phase 3 Deliverables/ project GitHub repository
Create Github Repository | Ava Johnson and Noah Morland | 100% | 2026-01-16 | 2026-02-20 | 36
Create README for github | Jaacob Lamoureux | 100% | 2026-02-21 | 2026-02-24
Finalize Gantt Chart | Jacob Lamoureux |  | 2026-02-14 | 2026-02-24 | 11
Finalize SOW | Jacob Lamoureux and Noah Morland | 100% | 2026-02-22 | 2026-02-23
Take code from lab and create final code document | Jacob Lamoureux | 100% | 2026-02-21 | 2026-02-22 | 2
Run 4 mix design scenarios | Jacob Lamoureux and Ava Johnson | 100% | 2026-02-23 | 2026-02-24
Create annotated code document | Noah Morland | 100% | 2026-02-21 | 2026-02-24 | 4
Phase 4 Report
Create and share document for report | Ava Johnson | 100% | 2026-02-13 | 2026-02-18 | 6
Methods | Noah Morland | 100% | 2026-02-19 | 2026-02-24 | 6
Results/ discussion | Ava Johnson |  | 2026-02-19 | 2026-02-24 | 6
References | Noah Morland, Jacob Lamoureux | 100% | 2026-02-19 | 2026-02-24 | 6
Formatting/ setup | Jacob Lamoureux | 100% | 2026-02-19 | 2026-02-24 | 6
Phase 5 Submittal
Upload SOW to Github | Jacob Lamoureux and Noah Morland | 100% | 2026-02-23 | 2026-02-24 | 2
Upload Gantt Chart to Github | Jacob Lamoureux |  | 2026-02-24 | 2026-02-24 | 1
Upload Code Document to Github | Jacob Lamoureux | 100% | 2026-02-22 | 2026-02-24 | 3
Upload ACD to Github | Noah Morland | 100% | 2026-02-24 | 2026-02-24 | 1
Upload Report to Github | Ava Johnson |  | 2026-02-24 | 2026-02-24
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.